## Sheet1
TASK NAME | START DATE | END DATE | DURATION
Software Engineering Project | 2021-08-27 | 2021-11-13 | 632h
Initial project Purposal | 2021-08-27 | 2021-08-31 | 40h
Installation of Python Enviroment | 2021-09-01 | 2021-09-03 | 24h
Install and Enable OpenCV | 2021-09-02 | 2021-09-03 | 16h
Design and Arch. Of the project | 2021-09-03 | 2021-09-30 | 224h
Literature Survey of various papers | 2021-09-03 | 2021-09-08 | 48h
Analysis of Methodology | 2021-09-09 | 2021-09-13 | 40h
Review and Evaluation of the project | 2021-09-14 | 2021-09-16 | 24h
Resource Implementation | 2021-09-15 | 2021-09-28 | 112h
Initial Prototyping / Frontend development | 2021-09-23 | 2021-09-27 | 40h
Review and Evaluation of face recognition | 2021-09-28 | 2021-09-30 | 24h
Development and Implementation of backend | 2021-10-01 | 2021-10-31 | 248h
Implementation changes with face recognition | 2021-10-01 | 2021-10-10 | 80h
Testing and Implementation of bug fixes | 2021-10-11 | 2021-10-16 | 48h
Review and Evaluation of backend to frontend | 2021-10-17 | 2021-10-19 | 24h
Implementation of relevant changes | 2021-10-20 | 2021-10-29 | 80h
System Testing | 2021-10-30 | 2021-11-06 | 56h
Documentation and Review | 2021-11-04 | 2021-11-13 | 80h